IMAT3903 Team Development Project

Assignment Log Book

Module tutor 	Matthew Dean mjdean@dmu.ac.uk

Name 			_____________________________________

P No			_____________________________________

Project Title		_____________________________________

Assessment Schedule _________ (A/B)

Deliverables and Feedback

- Sprints – roughly every four weeks starting in week 2 (See assessment schedule for dates of blog submission)

- Week 6 - Project Contract Friday 8th November 1pm via Turnitin - feedback returned by Fri 6th December

- Week 11 - Initial Deliverable Friday 13th December 1pm via Turnitin - feedback returned by Fri 31st January

- Week 27 - Final Report Friday 3rd April 1pm via Turnitin - feedback returned by Friday 22nd May

- Presentation schedule to be announced

Contents

Marking Schemes	1

Sprint Zero (5% of Module Grade)	1

Sprints (25% of Module Grade)	2

Product Contract (10% of module grade)	4

Initial Deliverable (15% of module grade)	5

Final Report (25% of module grade)	7

Presentation/Demo (20% of module grade)	9

Teams, Sprints, Scrums, the Friday Blog, your eGrid	10

Overview	10

Assessment Schedule	11

Benefits to you	13

Team Work	13

Team Engagement	13

Meetings	14

The Product Backlog	14

10 Minute Sprint Meetings	14

Scrum Meetings	14

The Friday Blog Entry	15

Sample Blog Entry	16

Your eGrid	17

So, Where to Start?	17

Submission of Work	17

Cheating / Plagiarism	17

Backups	17

Assessment Guide	18

What you need to do	21

Identifying the Cycle of Core Functionality	21

The Product	21

The System	21

Sprint Zero	22

Product Contract	22

Initial Deliverable	23

Final Report	24

Team Presentations	25

Appendices	26

Formatting Requirements	26

Some tips for your presentation	26

Re-Sit	26

# Marking Schemes

## Sprint Zero (5% of Module Grade)

|  |  | Clear fail <30% | Marginal fail 30-39% | Bare pass 40-49% | Clear pass 50-59% | Very good 60-69% | Excellent 70-79% | Outstanding >80% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Clarity of your role within team (80%) | You understand your role and have a clear idea of what you are doing |  |  |  |  |  |  |  |
| Completed Ethical review (20%) | You have engaged with the process of creating the ethical review for your project. Marks will not be awarded for this component until it has been fully completed to the satisfaction of your tutor! | 0% |  |  |  |  |  | 100% |

## Sprints (25% of Module Grade)

|  |  | Clear fail <30% | Marginal fail 30-39% | Bare pass 40-49% | Clear pass 50-59% | Very good 60-69% | Excellent 70-79% | Outstanding >80% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 |  |  |  |  |  |  |  |  |
| Written engagement | As evidence by your Friday blog |  |  |  |  |  |  |  |
| Verbal engagement | As evidenced by discussion |  |  |  |  |  |  |  |
| Evidence of work | As evidenced by work provided at the meeting |  |  |  |  |  |  |  |
| Sprint 2 |  |  |  |  |  |  |  |  |
| Written engagement | As evidence by your Friday blog |  |  |  |  |  |  |  |
| Verbal engagement | As evidenced by discussion |  |  |  |  |  |  |  |
| Evidence of work | As evidenced by work provided at the meeting |  |  |  |  |  |  |  |

|  |  | Clear fail <30% | Marginal fail 30-39% | Bare pass 40-49% | Clear pass 50-59% | Very good 60-69% | Excellent 70-79% | Outstanding >80% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint 3 |  |  |  |  |  |  |  |  |
| Written engagement | As evidence by your Friday blog |  |  |  |  |  |  |  |
| Verbal engagement | As evidenced by discussion |  |  |  |  |  |  |  |
| Evidence of work | As evidenced by work provided at the meeting |  |  |  |  |  |  |  |
| Sprint 4 |  |  |  |  |  |  |  |  |
| Written engagement | As evidence by your Friday blog |  |  |  |  |  |  |  |
| Verbal engagement | As evidenced by discussion |  |  |  |  |  |  |  |
| Evidence of work | As evidenced by work provided at the meeting |  |  |  |  |  |  |  |

## Product Contract (10% of module grade)

|  |  | Clear fail <30% | Marginal fail 30-39% | Bare pass 40-49% | Clear pass 50-59% | Very good 60-69% | Excellent 70-79% | Outstanding >80% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Identification of core functionality 20% | You have clearly identified appropriate core functionality that is distinct from your other team members |  |  |  |  |  |  |  |
| Product Justification 20% | There is clear justification as to why the product is required |  |  |  |  |  |  |  |
| Shared functionality 20% | There is appropriate and thoughtful consideration given to the boundaries between the product and the system |  |  |  |  |  |  |  |
| Social Impact Study (Proposal) 20% | There is an appropriate topic selected for the social impact study which addresses personal, national and international issues (state how) |  |  |  |  |  |  |  |
| Presentation 20% | The work is clearly presented, well written and signed off (See presentation requirements) |  |  |  |  |  |  |  |

## Initial Deliverable (15% of module grade)

|  |  | Clear fail <30% | Marginal fail 30-39% | Bare pass 40-49% | Clear pass 50-59% | Very good 60-69% | Excellent 70-79% | Outstanding >80% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Extended discussion of core functionality 10% | Clearly stated and appropriate for your product |  |  |  |  |  |  |  |
| Use Cases + Descriptions 10% | Well documentation, recognised appropriate notation clearly indicating interface requirements for product & core functionality |  |  |  |  |  |  |  |
| Class diagrams 10% | Well documentation, recognised appropriate notation clearly indicating programmatic requirements for product & core functionality |  |  |  |  |  |  |  |
| Sequence diagrams 10% | Appropriate notation with appropriate triangulation for product & core functionality |  |  |  |  |  |  |  |
| Entity Relationship Diagrams + Data Dictionaries 10% | Well documentation, recognised appropriate notation for product & core functionality |  |  |  |  |  |  |  |
| Other Appropriate Documentation 10% | Other documentation (e.g. rich pictures, storyboards, whatever you think is appropriate) |  |  |  |  |  |  |  |

|  |  | Clear fail <30% | Marginal fail 30-39% | Bare pass 40-49% | Clear pass 50-59% | Very good 60-69% | Excellent 70-79% | Outstanding >80% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proposed Testing Strategy 10% | Clear evidence of how you plan to implement the testing for your product/system |  |  |  |  |  |  |  |
| Smoke and Mirrors Prototype 10% | Functionality as indicated by use cases with clear indication of how the product matches with the use cases and addresses the core functionality |  |  |  |  |  |  |  |
| Proposed Security 10% | A sensible discussion of pertinent security issues |  |  |  |  |  |  |  |
| Bibliography 5% | A relevant and correctly cited bibliography |  |  |  |  |  |  |  |
| Presentation 5% | The report is professionally presented with clear sections, sub sections, page numbers and contents (See presentation requirements) |  |  |  |  |  |  |  |

## Final Report (25% of module grade)

|  |  | Clear fail <30% | Marginal fail 30-39% | Bare pass 40-49% | Clear pass 50-59% | Very good 60-69% | Excellent 70-79% | Outstanding >80% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Detailed discussion of core functionality of product 20% | A product has been created that is distinct from the shared system meeting the requirements of its core functionality. |  |  |  |  |  |  |  |
| Social Impact Study 15% | A thoughtful and well researched report on personal, national and global aspects of computer technology with a well constructed reading list using appropriate citation (Harvard) |  |  |  |  |  |  |  |
| Discussion of product development 10% | A detailed discussion of the development of key aspects of the product as they unfolded during the sprints |  |  |  |  |  |  |  |
| Final Documentation 15% | All documentation up to date and well presented |  |  |  |  |  |  |  |

|  |  | Clear fail <30% | Marginal fail 30-39% | Bare pass 40-49% | Clear pass 50-59% | Very good 60-69% | Excellent 70-79% | Outstanding >80% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Discussion of Shared Functionality 10% | Clear evidence of appropriate code reuse |  |  |  |  |  |  |  |
| Actual Testing Strategy 10% | Clear evidence of appropriate testing strategies |  |  |  |  |  |  |  |
| Implemented Security 10% | Appropriate consideration given to security |  |  |  |  |  |  |  |
| Module Review 5% | An interesting discussion of the module including what worked and what didn’t | 0% |  |  |  |  |  | 100% |
| Presentation 5% | The report is professionally presented with clear sections, sub sections, page numbers and contents (See presentation requirements) Word count appropriate +/- 10% |  |  |  |  |  |  |  |

## Presentation/Demo (20% of module grade)

Name:							Start Time:			End Time:

|  |  | Clear fail <30% | Marginal fail 30-39% | Bare pass 40-49% | Clear pass 50-59% | Very good 60-69% | Excellent 70-79% | Outstanding >80% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Core functionality 30% | Clear demonstration of core functionality distinct from shared components. |  |  |  |  |  |  |  |
| Appropriate duration 10% | Appropriate time was given for your part of the presentation |  |  |  |  |  |  |  |
| Appropriate coverage 10% | You gave a sensible presentation covered a good balance between your own individual product and how it integrates with the team’s system |  |  |  |  |  |  |  |
| Delivery 10% | The presentation was interesting and informative |  |  |  |  |  |  |  |
| Professionalism 10% | You displayed an appropriate level of professionalism |  |  |  |  |  |  |  |
| Product complexity 30% | The product meets the requirements in an effective professional manner |  |  |  |  |  |  |  |

# Teams, Sprints, Scrums, the Friday Blog, your eGrid

## Overview

The assessment model for this module comprises a set of practices drawn from industry, namely Agile Development.  Agile is an approach to project management used mainly (but not exclusively) in the realm of software development.

The following section explains how this works.

## Assessment Schedule

During the module you will be involved in a series of meetings. You will be sorted into teams and your team will be given an ID by your tutor. Your team’s ID is associated with an assessment schedule A or B.

In addition to the meetings you will also be required to submit blog entries.

Term 1

| Week | Deliverable/Action | Assessment Schedule A |  | Assessment Schedule B |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Sprint Meeting | Blog Entry | Sprint Meeting | Blog Entry |
| 1 |  |  | Y |  |  |
|  | Form teams, claim eGrid, select topic |  |  |  |  |
| 2 |  | Y | Y | Y | Y |
|  | Sprint zero deadline |  |  |  |  |
| 3 |  |  | Y |  | Y |
| 4 |  | Y | Y |  | Y |
| 5 |  |  | Y | Y | Y |
| 6 | Deadline for project contract |  |  |  |  |
| 7 |  |  | Y |  | Y |
| 8 |  |  | Y |  | Y |
| 9 |  | Y | Y |  | Y |
| 10 |  |  | Y | Y | Y |
| 11 |  |  | Y |  | Y |
|  | Deadline for initial deliverable |  |  |  |  |
| 12-14 | Xmas break |  |  |  |  |

Term 2

| Week | Deliverable/Action | Assessment Schedule A |  | Assessment Schedule B |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Sprint Meeting | Blog Entry | Sprint Meeting | Blog Entry |
| 15 |  |  |  |  |  |
| 16 |  |  | Y |  | Y |
| 17 |  | Y | Y |  | Y |
| 18 |  |  | Y | Y | Y |
| 19 |  |  | Y |  | Y |
| 20 |  |  | Y |  | Y |
| 21 |  |  | Y |  | Y |
| 22 |  |  |  |  |  |
| 23 |  |  | Y |  | Y |
| 24 |  | Y |  |  | Y |
| 25 |  |  |  | Y |  |
| 26 |  |  |  |  |  |
| 27 | Deadline for final report/system |  |  |  |  |
| 28-31 | Easter break |  |  |  |  |
|  | Presentation dates to be announced |  |  |  |  |

## Benefits to you

There are a number of benefits to approaching your software development assignments in this manner.  Firstly, the model is based on industrial practice; this means that when you enter the workplace you will have had some experience of Scrum/Agile development. Secondly, working in teams you will have fellow students around you as a peer support network. Thirdly, you will have regular meetings with your tutor to claim marks.  The regular meetings are an opportunity not only to show off your work but also to find errors/misconceptions, find solutions and obtain guidance on how to take your work to the next level.

To understand the assessment model there are some key concepts we need to cover.

They are...

- Team Work

- The product backlog

- 10 minute sprint meetings

- Scrum meetings

- The Friday Blog Entry

- eGrid

## Team Work

Team work is not group work! The typical model for group work involves a couple of group members who do all of the work, one student does nothing and then at the final assessment everybody is awarded the same grade.  Clearly this is not fair! The primary function of working in a team is to provide peer support (as is the case in the workplace).  Within a team, skills are typically unevenly distributed.  Some members may have skills in analysis and design; other may have skills in software development.  Clearly you don’t need to be completing each other’s work but you are strongly encouraged to help each other when support is needed.

At the start of the module you will be organised into teams of around four members.  Your team will be given an ID (A or B) this ID will identify your meeting schedule for the entire module (see schedule above).

It is the role of the team to ensure that each team member is working on different topics for the assessment.

## Team Engagement

To obtain the highest marks for team engagement you and your team must be seen to be actively engaging with the work for the module.  This means, for full marks, you need to be attending classes, engaging with the work and showing evidence of work completed out of class. Teams may be modified at any point during the module by your tutor.

## Meetings

Meetings are subject to standard University regulations.  Late meetings up to 14 days are capped at 40% after that a grade of 0% is automatically awarded.  If you have good reason to miss a meeting make sure you contact your tutor in good time and also provide appropriate evidence e.g. a Doctor’s note.

## The Product Backlog

The product backlog put simply is a to-do list of what work needs to be completed in order to complete the project.  As a team it is wise to draw this up so that each member knows what needs to be done next.  The backlog is not submitted as a deliverable but your tutor may want to look at over the year.

## 10 Minute Sprint Meetings

A sprint is a time limited period of activity where items from the product backlog are completed.

At the end of each sprint your team will be involved in a sprint meeting with your tutor.

For a sprint meeting your whole team needs to be in attendance.  Each team member will meet individually with your tutor to claim marks for work completed so far.  This meeting is an opportunity to seek feedback on work completed so far and gain ideas and inspiration from your tutor.  At each sprint meeting you need to have on screen your Friday blog entries completed to date (see below for addition details).

These meetings provide an opportunity to obtain provisional marks and feedback on work currently in development.

At various stages you will hand in your work via the normal mechanisms.  Your work will then be marked in the usual manner.

## Scrum Meetings

Scrum meetings are an opportunity for your team to meet, share ideas and work out plans of action for completing the product backlog.  As a minimum your team should be involved in one scrum meeting every week.

As a team you need to meet to discuss with each other what you have managed to accomplish individually.  A record of what is discussed at the meeting (minutes) should be taken along with a register of attendance.  Once completed these minutes should be distributed to all team members for inclusion in their individual Friday blog.    Weekly scrum meetings are the minimum requirement for peer support.  In an industrial setting scrum meetings typically occur every day (this is likely not practical for this work).

Scrum meetings should be brief and to the point, discuss what you need in as short a time possible to advance the project for each team member.

## The Friday Blog Entry

By the end of the module you will be required to submit a blog related to the work completed for the final assessment. (See assessment schedule for details of blog submission dates and requirements.)

The Friday Blog entry needs to be completed at the end of each week submitted before midnight (see above schedule for exact submission dates).

Blog entries need to be available via Blackboard and ready for your tutor to review. Any blog entries that are posted after the deadline of the previous Friday will not be considered as part of the sprint meeting and will be subject to the normal rules for submission of late submission.

Each blog entry should contain but not be limited to the following sections.

- Date and week number for the blog entry *

- Discussion of progress made

- Difficulties you have faced

- Work you plan to undertake next

- Attendance and minutes of team meetings *

- Peer review out of five of each team member’s performance for the sprints so far *

Make sure you use appropriate headings in the blog to makes sure the sections are clear.

Each blog entry is subject to a word count of 125 words (+-10%) items marked * above do not contribute to the final word count. It is probably a good idea to create your blog entry in Word first and then paste it into Blackboard when completed.

## Sample Blog Entry

Date and week number for the blog entry *

11th October 2019 Week 2

Discussion of progress made

This is the first week I am starting to get to know people and am now in a team for the assignment.  I hope that they work hard and they can help me when I am not sure.  I have started working on the lab work and it is starting to make sense but I really need to ask the tutor about a few things I am not so sure about.  I have a lot of other modules to think about too and it seems there is a lot of work here.  If I take things steadily and ask for help then I am sure I will be fine.  I need to set some time aside to read the material for next week to try and get ahead in case other issues start to get in the way.

(Word count 138)

(Notes: the word count is 125 word +- 10%.  You are aiming for 125 words but you could go as high as 138 or as low as 112.  If you type your blog entry in Word first it will tell you what your word count is for the text.)

Attendance and minutes of team meetings *

First meeting Monday 7th October 2019

In attendance Myself, Rod, Jane and Freddie

We had our first discussion about what we are going to do.  I think we have an idea of who is working on what project in the team.  Freddie had a problem claiming his eGrid, so he needs to contact the module leader to find out what to do.

Peer review out of five of each team member’s performance for the sprints so far *

Me		5 out of 5

Rod 		5 out of 5

Jane		5 out of 5

Freddie		5 out of 5

(Notes: Headings and sections marked * do not contribute to the word count.)

## Your eGrid

The eGrid is the mechanism by which your provisional and final grades are recorded.

The eGrid must be claimed in advance of the first sprint meeting, to do so go here...

https://g677.dmu.ac.uk/g677/

Your eGrid will be completed after each sprint meeting with grades awarded so far.  You have read-only access to the file but you may use it to model what grades you need to obtain in the future as you progress.

## So, Where to Start?

When all of these elements are written down, they actually start to sound a lot more complicated than they really are, so where to start?

- Sort yourself into a team of around 4 people

- Decide on a topic for the assessment – each team member needs to be working on a different topic

- Obtain your logbook and write your team ID on it

- Claim your eGrid and get used to downloading it from the web site

- Based on your team ID write in your calendar the dates of your meetings and blog entries

- Start your first Friday blog entry

- Attend your first sprint / scrum meeting

- Start the assignment

## Submission of Work

All work should be submitted via Turnitin or the blog on Blackboard unless told otherwise by your tutor.

## Cheating / Plagiarism

Although you are working collaboratively with others for this project all deliverables must be completed individually.  Any similarities between documentation will be assumed to indicate cheating.  Ensure that you are using appropriate citation (Harvard) when citing other people’s work.

## Backups

It is up to you to ensure that you keep appropriate backups of all work.  Loss of work due to backup failure is not normally considered reason for an extension.

# Assessment Guide

| Module name: |  | Team Development Project |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Module code: |  | IMAT3903 |  |  |  |  |  |  |
| Title of the Assignment: |  | Team Project |  |  |  |  |  |  |
| This coursework item is both: |  |  |  | Summative |  |  | Formative |  |
| This summative coursework will be marked anonymously Initial Deliverable + Final report All other components |  |  |  |  |  | Yes No |  |  |
| The learning outcomes that are assessed by this coursework are: 1. Analyse and document a problem producing a suitable set of supporting documentation 2. Develop software of significant complexity 3. Test the software using rigorous testing strategies 4. Research theory associated with the software in question including personal, national and international issues 5. Work as a team |  |  |  |  |  |  |  |  |
| This coursework is both: |  |  | Individual |  |  |  | Group |  |
| Assessment will mainly be based on a series of one to one meetings over the year. Team engagement will also be reviewed at these meetings. Meeting will be documented by an on-going blog of activities and dialogue with the tutor. |  |  |  |  |  |  |  |  |
| This coursework constitutes 100% to the overall module mark. |  |  |  |  |  |  |  |  |
| Date Set: | Week 1 |  |  |  |  |  |  |  |
| Date & Time Due: | See above |  |  |  |  |  |  |  |
| Your marked coursework and feedback will be available to you on: If for any reason this is not forthcoming by the due date your module leader will let you know why and when it can be expected. The Head of Studies (headofstudies-tec@dmu.ac.uk ) should be informed of any issues relating to the return of marked coursework and feedback. Note that you should normally receive feedback on your coursework by no later than four working weeks after the formal hand-in date, provided that you met the submission deadline. |  |  |  |  | See above |  |  |  |
| When completed you are required to submit your coursework to: - Electronically via Turnitin |  |  |  |  |  |  |  |  |

| Late submission of coursework policy: Late submissions will be processed in accordance with current University regulations which state: “the time period during which a student may submit a piece of work late without authorisation and have the work capped at 40% [50% at PG level] if passed is 14 calendar days. Work submitted unauthorised more than 14 calendar days after the original submission date will receive a mark of 0%. These regulations apply to a student’s first attempt at coursework. Work submitted late without authorisation which constitutes reassessment of a previously failed piece of coursework will always receive a mark of 0%.” |  |
| --- | --- |
| Academic Offences and Bad Academic Practices: These include plagiarism, cheating, collusion, copying work and reuse of your own work, poor referencing or the passing off of somebody else's ideas as your own. If you are in any doubt about what constitutes an academic offence or bad academic practice you must check with your tutor. Further information and details of how DSU can support you, if needed, is available at: http://www.dmu.ac.uk/dmu-students/the-student-gateway/academic-support-office/academic-offences.aspx and http://www.dmu.ac.uk/dmu-students/the-student-gateway/academic-support-office/bad-academic-practice.aspx |  |
| Tasks to be undertaken: See below |  |
| Deliverables to be submitted for assessment: See below |  |
| How the work will be marked: See below |  |
| Module leader/tutor name: | Matthew Dean |
| Contact details: | mjdean@dmu.ac.uk |

# What you need to do

During this module each team member will develop an individual product of significant complexity.  The product will exist in the context of a shared system created by you and your team.

Your product will have clearly defined core functionality.  It needs to serve a clear set of business requirements of suitable size and complexity that are distinct from the shared system and the products being created by others in your team.

This module is an opportunity for you to shine and demonstrate what you have learnt over the last two/three years.  There is little taught content for the module however your tutor will facilitate your learning by appropriate advice and support.  Outside of this your tutor’s primary role is to assess your progress and performance both as a team and as an individual.

The system should be designed in such a way as to facilitate robust testing, code re-use and appropriate documentation.  At the start of the module you will form teams of around 4 (no more than 5 and no less three!) and create your initial product backlog.  Over typically a four-week period your team will perform sprints.  A sprint will involve the completion of important components from the backlog.  There will be four sprints over the year.  At the end of the year you will give a presentation of work completed and produce a report documenting your achievements.

## Identifying the Cycle of Core Functionality

The cycle of core functionality identifies the primary use cases upon which your system and project success will be judged.  It is described as a cycle in that the user inputs some data into the system, this is then processed and some sort of output comes back to the user. For example, if you are creating an on-line bookshop your system must allow the purchase of books.  The user places an order, the back end processes the order and the user receives their book(s). This core functionality must then be supported by other use cases such as customer sign up, payments and processing of sales by staff.  These tasks must be carried out in a professional effective manner.  Completion of non-core functionality to the expense of the core aspect may severely reduce your project grade.

## The Product

The product is an individual unit of software + documentation constructed for a client.  It serves specific needs of that client meeting a set of business requirements.  Each individual is responsible for their own final product.

The product may be any item of substantive software development e.g. a database for a chess club.  Products may be sourced from external clients, companies, friends, family, internal clients, members of DMU staff or they may be self proposed.

## The System

The system is a set of software + documentary artefacts seen from the point of view of the developers in your team.  Clients are not aware of your software systems, nor do they care about them.  As developers you need to create software systems that reduce duplication of effort, allow for rigorous security, testing and documentation with a clear eye to code re-use.  The system will grow out of the individual products.

## Sprint Zero

The first sprint begins in week 1 of the module. The first part of the sprint is referred to as sprint zero this is where various aspects of the assessment are set up. At the beginning of the module you will be allocated an assessment schedule (A or B).  This allocation will indicate the deadlines for all future sprints/activities.

By the end of week 2 you will be expected to have allocated roles within the team and made a start on your ethical review.

Sprint Zero activities:

- Set up your teams

- Decide on your topics (system and social impact study)

- Claim your eGrids

- Create your initial product backlog

- Begin work on your ethical review

No blog entry is required for sprint zero!

## Product Contract

A product contract is to be produced by each individual in the team outlining details of what that individual plans to do.  The product contract will contain the following information:

The contract must be submitted as a single word document with any diagrams clearly included as part of the document.

- A cover page detailing

  - Your name

  - Your P number

  - Course

  - Product title

  - Team members

- Identification of core functionality + supporting use cases

- Product justification including details of client / proposer

- Discussion of shared components of the product with other team members

- Topic and Description of Social Impact Study

- Approved Ethical Review including signatures of both student & tutor

See the web site for a pro forma of the contract, ethical review and a sample consent form.

## Initial Deliverable

The initial deliverable is an individual report containing all of the analysis and design for the product / system.

The initial deliverable must be submitted as a single word document with any diagrams clearly included as part of that document. Any additional code, e.g. prototype must be zipped up and submitted as a separate file.  Any work that is in Enterprise Architect etc, that is not included in the main report will be awarded zero marks. The report must flow as a report with appropriate discussion providing context for all diagrams.

The initial deliverable will contain the following sections plus anything else you consider appropriate:

- A cover page detailing

  - Your name

  - Your P number

  - Course

  - Product title

  - Team members

- Extended discussion of proposed core functionality

- A discussion of how your product integrates with the team’s system

- Initial bibliography for social impact study (Created from your initial literature search using appropriate notation)

- Use case diagrams + descriptions and discussion identifying what the product will do

- Screen shots and discussion of the smoke and mirrors prototype explaining how it addresses the proposed use cases

- Class diagrams with discussion identifying how the system functionality will be addressed

- Sequence diagrams with discussion indicating how classes and use-cases integrate with each other

- Entity Relationship Diagrams, Data Dictionaries plus discussion

- Other Appropriate Documentation (including appropriate discussion)

- Discussion of testing + usability testing carried out so far

- Discussion of security considerations

- Code for product / system

It is recommended that you make appropriate use of appendices where the documentation becomes repetitive (e.g. testing and use case descriptions).  Include only appropriate samples with discussion in the main body with more detailed examples in the appendix.

## Final Report

The final report must be submitted as a single word document with any diagrams clearly included as part of that document. Any additional code, e.g. prototype must be zipped up and submitted as a separate file.  Any work that is in Enterprise Architect etc, that is not included in the main report will be awarded zero marks. The report must flow as a report with appropriate discussion providing context for all diagrams.

The final report will contain but not be limited to:

- A cover page detailing

  - Your name

  - Your P number

  - Course

  - Product title

  - Team members

- Detailed discussion of the implemented core functionality relating it to system documentation

- Social Impact Study (3000 +-10% words) see below for formatting guidelines

- Discussion of system changes based on progress against backlog

- Final Documentation with appropriate discussion

- Discussion of and examples of implemented testing

- Discussion of and examples of implemented security

- Discussion of shared functionality with examples

- Module Review

- Code for product / system

It is recommended that you make appropriate use of appendices where the documentation becomes repetitive (e.g. testing and use case descriptions).  Include only appropriate samples with discussion in the main body with more detailed examples in the appendix.

## Team Presentations

At the end of the module your team needs to make a presentation of all work completed during the year.  There is no set structure for the presentation but it is important that all members have equal time and all aspects of the system both shared and individual receive appropriate coverage.

# Appendices

## Formatting Requirements

A word document is available on the module web site for formatting the following major deliverables:

- Initial Deliverable

- Final Report

Each document must be created using single sided A4 using 1.5 line-spacing, Arial 12pt font, 2.5cm margins left and right.  Make sure that all content is legible and diagrams are large enough to be read clearly.  All deliverables must be spirally bound with professional covers. Table of contents should be included with correct page numbering.  Any references to external sources of information must be evidenced by Harvard referencing with an appropriate reading list at the end of the report.  Make sure that all work is proof read for errors in grammar and spelling.

Your report must have a reading list with appropriate citations.  The reading list may make use of 20% web sources.  The remaining 80% must come from non web sources e.g. books and journals.

The word count for the social impact study is 3000 (+-10%) words.  You must specify the actual word count at the start of the social impact study.  There is an allowable margin of 10% either way.

## Some tips for your presentation

Try and relax and take your time.  This will be difficult but it will help you to do a better job.  If you overrun, you are likely to be cut short. It is unlikely that you will have time to show off all of your work so concentrate on the most important use cases, i.e. the core of the system.

Start the demo by stating your name and the title/reason for your project make no assumptions about any prior knowledge the marking tutors have.  There is no dress code as such but you will feel better and leave a better impression if you wear something smart for the day.

If something goes wrong during the demo or you can't answer a question don't panic.  If your system goes wrong, then try and move onto something else.  If you don't understand a question, then ask for the question to be re-phrased.  You may wish to bring your own computers in on the day.  This gives you more control over the software and allows you to test your system in advance.  Whatever machine you use ensure you test your system in advance and do not make any last-minute changes to your system!  If in doubt check with the technicians first to make sure everything you want to use on the day works correctly.

## Re-Sit

In the case of needing to re-sit the module you will be required to re-submit any failed components which will typically be capped at 40%.  You will not be required to attend any sprint meetings but the blog will need to be brought up to date should it be one of the failed components.